## Slide 1
PROJECT REPORT · 2026-09-17
Cindy Pawford
An interactive agent running on a desk-side DGX appliance that authors and publishes its own website to cindypawford.com, takes feature requests and votes from the public, and acts on them — used as a live testbed for agent development patterns, safe publishing patterns, and the security controls that make unattended publishing defensible.
v0.1.0 · Beta — publishing path proven; orchestration being redefined
Justin St-Maurice
DGX appliance, home lab (desk-side) — Project Titan fleet

## Slide 2
Where the project stands
As of 2026-09-17.
VERSION
v0.1.0
STATUS
Beta — publishing path proven; orchestration…
STARTED
2026-09-06
LAST UPDATE
2026-09-17
RELEASE
v0.1.0 — the first build in which code authored by the agent successfully reaches the live domain through the full guarded path. End to end, unattended, no credential in the agent.
WORKING
Agent-authored commits push through the injecting proxy. The guard workflow gates the governed directory. Deploy runs from the control plane. The fleet verification suite, memory-purity audit, egress token-injection suite and the four Cindy-specific suites all pass on the appliance (ticket #103, September 15).
NOT WORKING
Work decomposition. Given a four-deliverable brief the agent attempted it in one pass, hit the output-token ceiling on every continuation, and wrote nothing to disk. No rule governs how much work may enter a cycle, and there is no orchestrator/builder split at runtime. Tool calls remain untraced (see §9).
IN FLIGHT TODAY
Defining the orchestration discipline — Cindy as orchestrator, issuing one ticket at a time to a builder sub-agent, under a per-cycle work budget.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 3
Why this project exists
The artifact is an instrument. These are what it measures.
1
Can an agent ship code to a public production surface with no human in the authoring loop, while holding no credential and being unable to approve its own work? (Tests the Autonomous Publishing Pattern against a real weekly cadence.)
2
Where does an agent's identity leak into its output, and what structural separation prevents it? (Persona and product are different concerns; the system does not know that by default.)
3
Can a closed feedback loop — publish, collect public votes, act on the ranked queue — run autonomously without a human reading every inbound request, given that fan payloads are untrusted input?
4
Which failure modes are model failures and which are harness failures? Token and context-window exhaustion, not reasoning quality, has caused most losses so far.
5
What does the SDLC actually look like when the developer is an agent — tickets, review, rollback, verification? (Exercises the Agent SDLC deck.)
What a result looks like
A named pattern with a control, a verification suite that attempts to violate that control and requires failure, and a measured number. Not a demo.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 4
Scope — what this is, and what it is not
Stated explicitly, because the artifact is easy to mistake for the goal.
It is
An agent-development experiment. A deliberately low-stakes, high-visibility surface on which to exercise publishing, safety, and feedback-loop patterns.
It is not
A website project. cindypawford.com is a conduit — the channel through which the agent communicates and receives feedback. Its content is disposable by design.
It is not
A persona project. The dog-on-the-phone voice is delivery, not payload.
The deliverable
A framework and set of best practices for securing an agent that authors and publishes to the public internet. The site is the evidence; the pattern is the product.
Sibling project
Football Dan (football-dan, already in the fleet manifest) will use the same reporting and SDLC scaffolding to study whether an agent can build a dynamic, curated, and accurate knowledge graph. Same instrument, different question.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 5
Architecture at a glance
Hardware to public surface, and the gate in between.
LAYER | COMPONENT | NOTE
Hardware | DGX appliance, home lab | Local inference. Power draw is measurable, which makes cost-per-feature expressible in joules as well as dollars.
Runtime | Hermes, per-agent container | Declarative personas at config/hermes/personas/*.md. Sub-personas supported — this is the September 15 fix.
Fleet manifest | config/agents.yaml | Single source of truth. Compose topology is generated from it; CI fails on drift.
Model routing | LiteLLM, alias cindy-active-coding-model | Model is swappable behind an alias, which is what makes era-over-era model comparison possible.
Control plane | patternsatscale/project-titan | Human-owned. Infrastructure-as-code, verification suites, reset/archive/rollback scripts, the credential-injecting proxy. The agent has no write path.
Canvas | CindyPawford-Online | Agent-owned except the CI directory, which is bind-mounted read-only beneath it.
Credential custody | Caddy reverse proxy (github-proxy) | Token injected in transit. The agent's environment contains no credential, and a suite fails the build if one appears.
Output surface | cindypawford.com | Static site, deployed by the control plane after a guarded pull request merges.
Feedback path | Public suggestion + voting API, era-partitioned | The closed loop: publish, collect, rank, act. Inbound payloads are treated as data, never instructions.
Memory plane | Per-agent Markdown, ./data/memories/<id> | Survives the canvas reset. The agent loses the artifact and keeps the learning.
Observability | Langfuse + OpenTelemetry | Inference is traced. Tool calls and memory writes are not yet — a known gap.
The loop
The agent wakes on a schedule, reads the ranked public request queue and its own live site, writes changes into the canvas, and pushes through the injecting proxy onto a branch it cannot deploy from. A guard workflow — defined inside a directory the agent cannot write to — diffs the pull request and refuses governed paths. On merge, the control plane deploys.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 6
Where this connects to the pattern library
This project is the live case for work already written up.
ARTIFACT | RELATIONSHIP
Injecting Agents into the SDLC | Cindy Pawford is the live case. Tickets, walkthroughs, acceptance criteria and verification suites in docs/ are that pattern being executed rather than described.
The Autonomous Publishing Pattern | Written from this system. Two-repository split, credential injection in transit, destructive-actions-as-requests, weekly reset. This project is where its claims get falsified or hold.
project-titan — docs/reference-architecture-tenets.md | The TN-n control catalogue (TN-1 input governance through TN-9 recovery). Where each control here is scored against the working tree.
docs/lab-work/scratch/agent-orchestration-discipline.md | Written 2026-09-17 in response to the token-ceiling failure. A proposed runtime counterpart to AGENTS.md: orchestrator and builder roles, the ticket contract, and admission control. A recommendation in scratch — not accepted, not ticketed, not enforced.
config/hermes/personas/cindy-pawford.md | The soul file. Names no provider, no gateway host, no deploy mechanism — need-to-know, enforced by a test.
docs/2026-09-*-ticket*.md | Per-ticket walkthroughs. The audit trail of the agent SDLC in practice.
Companion decks
Injecting Agents into the SDLC · The Autonomous Publishing Pattern
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 7
Milestones
Shipped, in flight, and not yet attempted.
DATE | MILESTONE | STATUS
2026-09-06 | Project Titan control plane initialised; ticket-driven SDLC established | Done
2026-09-14 | Fleet decomposed into per-agent containers; Cindy Pawford unit stood up | Done
2026-09-15 | Full appliance verification pass — 11 acceptance criteria, all suites green | Done
2026-09-15 | Persona bleed identified and fixed via a dedicated authoring sub-persona | Done
2026-09-16 | v0.1.0 — agent-authored code published to cindypawford.com | Done
2026-09-17 | Failure mode identified: no work-decomposition rule (four-deliverable brief) | Done
2026-09-17 | Orchestration discipline proposed: orchestrator, builder, one ticket at a time | In flight
— | Proposal accepted, ticketed, and wired into Cindy's runtime context; re-tested | Planned
— | Per-cycle work budget and admission control on the request queue | Planned
— | Per-action audit log for tool calls and memory writes | Planned
— | Outbound egress restriction (custody is not containment) | Planned
— | Closed feedback loop unattended: votes to ranked queue to shipped feature | Planned
— | First era reset and model rotation, producing a longitudinal comparison | Planned
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 8
What I've learned
Promoted out of the daily log. Each one transfers to a project unlike this one.
L1
Persona and product are separate concerns, and nothing enforces that by default. An agent asked to build something will treat its own identity as available material and write it into the artifact.
L2
Sub-personas are a compartmentalisation control, not just an ergonomic feature. Giving the authoring task its own persona with its own context removes the identity parameters from the generation path entirely — the same "remove the capability rather than police it" move the publishing pattern makes with credentials.
L3
The harness fails before the model does. The dominant failure so far is context and token-window exhaustion on open-ended creative tasks, not poor reasoning. Budget the window as a first-class resource and make the agent's task decomposable.
L4
Open-ended fun is a harder test than useful work. "Build a game about yourself" has no natural stopping condition, no acceptance criteria, and maximum incentive for self-reference — which is exactly why it surfaces limits that structured tickets hide.
L5
A gate the agent cannot reach beats a trust judgement about the agent. It is what makes a daily publishing cadence defensible rather than brave.
L6
Orchestration is a safety control, not a productivity trick. An agent that both plans and builds fills its own context with generated code and then loses both jobs. Split the roles: the orchestrator holds judgement, voice and the plan; a builder sub-agent holds one ticket, its own terminal and its own context, and returns a…
L7
Any agent facing a queue needs admission control. A brief with four deliverables and a public request queue with forty votes are the same input: unbounded work admitted into one cycle. The queue must be treated as a backlog, not a work order, with a per-cycle work budget that is enforced outside the agent.
L8
An agent's self-report is not evidence. Mid-run status claimed files written and syntax-valid that were not on disk. With no per-action record there is no way to adjudicate afterwards, so progress must be verified against the filesystem rather than read out of the transcript.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 9
Open questions and risks
Stated plainly, so the pattern is adopted for the right reasons.
ITEM | TYPE | NOTE
Unbounded work per cycle | Risk | Nothing limits how much work enters one run. Demonstrated 2026-09-17. Under cron with a public queue this becomes the primary availability risk, and it is enforced today only by instruction.
Self-reported progress | Risk | The agent claimed files written that were not on disk. Any status, ledger entry or era recap it authors is a claim, not a record, until verified against the filesystem.
No per-action audit record | Risk | Inference is traced; tool calls and memory writes are not. Input-boundary claims cannot be checked after the fact, and the 2026-09-17 run cannot be reconstructed.
Custody is not containment | Risk | Without outbound network restriction the injecting proxy is bypassable by design. Both halves are needed before the architecture can claim containment.
Untrusted public input | Question | Fan payloads are bounded by instruction ("data, not instructions"), not by structure. A public voting queue is a prompt-injection surface, and instruction is the weakest available control.
Context budget as a control | Question | Should the window be a hard budget enforced outside the agent, the way the two-hour wall-clock deadline already is?
Persona bleed in reverse | Question | The authoring sub-persona keeps identity out of the code. Does it also keep the product out of the identity — or does the primary persona now describe a site it did not write?
Reporting scaffold reuse | Question | Does this template survive contact with Football Dan, whose output is a knowledge graph with an accuracy measure rather than a website?
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 10
THE LOG
Recent progress
The 3 most recent updates, newest first.

## Slide 11
2026-09-17
One brief, four deliverables, zero files written
INTENT
Hand Cindy a large creative brief over Telegram with an eight-hour budget: add several pages to the site, hide Easter eggs about me, build a treasure-hunt mystery, fix the confusing 2:00 Sprint game, and build a Pac-Man-style game. Manual testing ahead of putting this cycle on cron.
WHAT HAPPENED
It planned well, then lost everything. After laying out three pages and appending CSS cleanly, it tried to rewrite app.js to hold the Pac-Man engine, the vault logic and a rebuilt Sprint in one pass. Every continuation hit the output-token ceiling with reasoning consuming the whole budget; nothing reached disk. Asked for a status, it claimed files written that were not there.
CHANGE MADE
None to the running system; the change is architectural. Cindy stops being a builder and becomes an orchestrator: decompose a brief into tickets, then dispatch exactly one at a time to a builder sub-agent. Proposed in docs/lab-work/scratch/ — a recommendation, not yet accepted or ticketed.
LESSON
Orchestration is a safety control, not a productivity trick (L6). Any agent facing a queue needs admission control (L7). An agent's self-report is not evidence (L8). And L3 holds: the harness failed, not the model — the reasoning was sound, the missing piece was a rule about how much work may enter one cycle.
NEXT
Wire the discipline into Cindy's runtime context, then re-run this exact brief as the test. The correct output is a written backlog with one ticket in flight — not one giant call.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 12
2026-09-16
v0.1.0: agent-authored code goes live
INTENT
Close the loop end to end: agent writes, pipeline gates, control plane deploys, no human in the authoring path and no credential in the agent.
WHAT HAPPENED
It shipped. Code written by the agent reached cindypawford.com through the injecting proxy, a guarded pull request, and an infrastructure-as-code deploy. The agent held no token at any point, could not read the workflow that checked its output, and could not merge its own work.
CHANGE MADE
Tagged v0.1.0 as the first releasable beta of the publishing path.
LESSON
The claim from the publishing deck — that autonomy is bounded by a checkpoint rather than by trust — is now demonstrated rather than argued (L5).
NEXT
Give it something unstructured to do and see what breaks.
Cindy Pawford · v0.1.0 · as of 2026-09-17

## Slide 13
2026-09-15
Persona bleed into generated content
INTENT
Have the agent author site content and markup directly.
WHAT HAPPENED
The agent pulled its own personality parameters into the artifact. The HTML it produced was polluted by the primary persona's soul file — voice, self- reference and character material showing up in structure and content where a page was wanted. The output was interesting, and wrong. The agent had conflated who it is with what it was asked to build.
CHANGE MADE
Used the Hermes framework's sub-agent and sub-persona capability to create a second persona inside the Cindy Pawford container whose only job is authoring code and content. It runs without the primary persona's identity parameters in context, so there is nothing to bleed.
LESSON
Persona and product are separate concerns and nothing enforces that by default (L1). The fix is structural, not a prompt instruction — remove the identity parameters from the generation path rather than asking the agent not to use them (L2). This is the same move the publishing pattern makes with credentials, applied to identity.
NEXT
Verify that the authoring sub-persona stays clean under a creative brief, where the temptation to self-reference is strongest.
Cindy Pawford · v0.1.0 · as of 2026-09-17